## Audit Tracking Dashboard
YEAR-END AUDIT SCHEDULES TRACKING MASTER
Financial Year: 2025-26 ¦ Target Audit Sign-Off Date: June 15, 2026
TOTAL SCHEDULES |  |  | COMPLETED |  | IN PROGRESS | NOT STARTED
Audit Readiness Summary by Process Domain
Audit Process Area | Total Line Items | Completed | Pending Review | Completion %
Fixed Assets
Trade Receivables
Trade Payables
Inventory & Warehouse
Tax Compliance
Treasury & Bank Operations
Human Resources & Payroll
Total Enterprise Portfolios

## Detailed Audit Schedules
Year-End Detailed Audit Schedules & Deliverables Matrix
Audit Area / Domain | Schedule / Deliverable Name | Process Owner | Target Due Date | Actual Completion Date | Current Status | Reviewer Sign-Off | External Audit Sample Ref | Comments / Observations / Blockers
Fixed Assets | Fixed Asset Register (FAR) vs General Ledger Reconciliation | Finance Manager | 2026-05-15 | 2026-05-14 | Completed | Approved | FA-SAM-01 | Depreciation variables validated under Companies Act Schedule II rules.
Fixed Assets | Physical Verification Report of Capitalized Plant Assets | Plant Controller | 2026-05-20 |  | In Progress | Pending Review | FA-PV-04 | Field verification 85% completed. Tracking 2 minor scrap variances.
Trade Receivables | Debtors Ageing Breakdown & Balance Confirmation Letters | AR Lead | 2026-05-10 | 2026-05-09 | Completed | Approved | AR-CONF-11 | Top 25 accounts confirmed directly. No material variances logged.
Trade Receivables | Expected Credit Loss (ECL) Provisioning Matrix calculation | Risk Head | 2026-05-25 |  | Not Started | Pending | AR-ECL-02 | Awaiting final macro-economic input parameters from treasury.
Trade Payables | Trade Creditors Reconciliations & MSME Classification Checks | AP Manager | 2026-05-18 | 2026-05-19 | Completed | Pending Review | AP-MGT-09 | MSME status checked against government portal registrations.
Inventory & Warehouse | Year-End Physical Stock Take Summary & Cut-off Analysis | Supply Chain Lead | 2026-05-12 | 2026-05-12 | Completed | Approved | INV-ST-2026 | Third-party audit team was present at central warehouse location.
Inventory & Warehouse | Slow-Moving and Obsolete Inventory Provisioning Model | Finance Manager | 2026-05-28 |  | In Progress | Pending | INV-OBS-02 | Reviewing stock item movements older than 180 days.
Tax Compliance | Deferred Tax Asset (DTA) & Liability (DTL) Computation Sheet | Tax Head | 2026-06-02 |  | Not Started | Pending | TAX-DT-01 | Dependent on final depreciation numbers from Fixed Asset tab.
Tax Compliance | Statutory TDS / TCS Return Reconciliations with Form 26AS | Tax Accountant | 2026-05-15 | 2026-05-16 | Completed | Approved | TAX-26AS-M | Form 26AS matching rate is currently at 99.4% variance resolution.
Treasury & Bank Operations | Bank Reconciliation Statements (BRS) for All Active Accounts | Treasury Lead | 2026-05-05 | 2026-05-04 | Completed | Approved | TR-BRS-ALL | All 14 bank lines fully matched to the general ledger balance.
Treasury & Bank Operations | Foreign Exchange Exposure & Mark-to-Market (MTM) Valuation | Treasury Lead | 2026-05-22 |  | Overdue | Pending | TR-FX-M7 | Awaiting final rate configurations from clearing bank parameters.
Human Resources & Payroll | Full & Final Settlement Provisions & Gratuity Valuation Actuarial Report | HR Operations | 2026-05-25 |  | In Progress | Pending Review | HR-ACT-01 | External actuary has initiated study; report expected by May 24.
Human Resources & Payroll | Director Compensation Disclosure Verification and Form 16 Links | Company Sec. | 2026-06-05 |  | Not Started | Pending | HR-DIR-COMP | Board notes drafted. Waiting for nomination committee final closure.